## Deliverables Register
BDSI Deliverables Register -- Gift ¦ Q2 2026
All output files produced by the team, linked to KPI area. Update version and status as files evolve.
# | File Name | Folder Path | Version | Date | KPI | KPI Area | Status | Notes
1 | Metadata_SOP_Revised_Phase1.docx | 02_DataDriven_15pct\Data_Infrastructure\Chat_to_Data | v1.0 | 2026-05-26 | D1 | Data-Driven Org | Final | Revised SOP -- clean policy doc
2 | Datahub_metadata_template.xlsx | 02_DataDriven_15pct\Data_Infrastructure\Chat_to_Data | v1.0 | 2026-05-26 | D1 | Data-Driven Org | Final | 52 cols, A-H core + AI cols AR-AZ
3 | SOP_ChangePoints_WorkingTeam r3.pptx | 02_DataDriven_15pct\Data_Infrastructure\Chat_to_Data | r3 | 2026-05-26 | D1 | Data-Driven Org | Final | 25-slide change briefing deck
4 | Data_Quality_Monitoring_Report.xlsx | 02_DataDriven_15pct\Data_Infrastructure\DQ_Framework | v1.0 | 2026-05-26 | I2 | Monitoring | Final | 4-sheet: Incident+Log+Problem+KPI
5 | DQ_Management_Report.pptx | 02_DataDriven_15pct\Data_Infrastructure\DQ_Framework | v1.0 | 2026-05-26 | I2 | Monitoring | Final | 8-slide mgmt presentation
6 | Incident_Management_Flow.pptx | 02_DataDriven_15pct\Data_Infrastructure\DQ_Framework | v1.0 | 2026-05-26 | I2 | Monitoring | Final | 8-slide reactive+proactive flow
7 | Draft Incident Management Track.xlsx | 05_Monitoring_10pct | v1.0 | ongoing | I2 | Monitoring | Active | SDP ticket log -- update weekly
8 | RBAC for UAM.xlsx | 04_DataGovernance_30pct\UAM_RBAC | v1.0 | 2026-03-26 | I1 | Data Governance | Final | Phase 1 RBAC matrix
9 | Tenant_Recategory_Impact_SummaryList_BDSI.xlsx | 03_ProjectLead_25pct\03a_Impact_Projects_15pct\Tenant_Recategory | v1.0 | 2026-05-26 | D2 | Project Lead | Active | 6 sheets -- impact + timeline
10 | MIS Task List_Re Category Tenant Downstream 11 May 26.xlsx | 03_ProjectLead_25pct\03a_Impact_Projects_15pct\Tenant_Recategory | v1.0 | 2026-05-26 | D2 | Project Lead | Active | Downstream impact task list
11 | DS and MIS - Project 2026 8 May 26.xlsx | 03_ProjectLead_25pct\03b_BAU_MIS_10pct | v1.0 | 2026-05-26 | D3 | BAU/MIS | Active | 2026 project roadmap + MIS tasks
12 | Personal_KPI_Tracker.xlsx | 00_Master_Tracking | v2.0 | 2026-05-26 | ALL | All KPIs | Active | Self-assessment tracker with scoring criteria
13 | BDSI_Master_Tracker.xlsx | 00_Master_Tracking | v1.0 | 2026-05-26 | ALL | All KPIs | Active | This file -- single source of truth
14 | SOP_Data Stewardship Management Procedure_ENG_26.03.26.pdf | _Reference | signed | 2026-03-26 | I1 | Data Governance | Reference | Official signed SOP -- read only

## Project Tasks
Project Task Tracker -- Active Projects Q2 2026
Update % Done and Status weekly. Flag blockers early.
Project | Workstream | Task | Owner | Target Date | Status | % Done | Blockers | Notes
Tenant Recategory | Impact Validation | 1. Validate daily TUID after Brand Master delivery (21 May) | Gift | 2026-05-31 | Planned | 0% | Waiting for DE Brand Master | Col H in SDP if repeat issue found
Tenant Recategory | Impact Validation | 2. Prepare Segment Maintenance (lotion script) | Gift | 2026-06-15 | Planned | 0% |  | Depends on Brand Master validation passing
Tenant Recategory | Impact Validation | 3. Tenant DA Group Category mapping update | Gift | 2026-06-30 | Planned | 0% |  | Downstream from segment maintenance
Tenant Recategory | Reporting | 4. Confirm all BDSI reports unaffected post-cutover | Gift | 2026-06-30 | Planned | 0% |  | Sign-off required before closing project
Data Governance | UAM/RBAC | RBAC matrix Phase 1 complete + data owner sign-off | Gift | 2026-06-30 | In Progress | 7000% |  | RBAC for UAM.xlsx -- Phase 1 as-is done
Data Governance | Metadata | Datahub template A-H core complete | Gift | 2026-04-30 | Done | 10000% |  | Datahub_metadata_template.xlsx v1.0
Data Governance | Metadata | AI project cols AR-AZ complete + usable by Chat-to-Data | Gift | 2026-06-30 | In Progress | 8000% |  | Chat-to-Data team to validate adoption
Data Governance | DQ Framework | 7-dimension health check framework operational | Gift | 2026-05-31 | In Progress | 8500% |  | Monitoring report + flow delivered; checks need running
Data Governance | Incident Tracking | Incident flow published + SDP log active | Gift | 2026-05-31 | Done | 10000% |  | Incident_Management_Flow.pptx + Draft Track
MIS/BAU | Dashboard | BAU dashboard: nonGP tenant sale module added | Gift | 2026-06-30 | Planned | 0% |  | New module for KPI D1 evidence
MIS/BAU | Dashboard | BAU dashboard: Car traffic module added | Gift | 2026-06-30 | Planned | 0% |  | New module for KPI D1 evidence
MIS/BAU | Dashboard | BAU dashboard: Calendar master module added | Gift | 2026-06-30 | Planned | 0% |  | New module for KPI D1 evidence
MIS/BAU | BU Adoption | Finance/Operations team walkthrough + regular use confirmed | Gift | 2026-06-30 | Planned | 0% |  | Key evidence for KPI D1 score 4+
MIS/BAU | MIS Tasks | Weekly MIS task update sent to team lead | Gift | ongoing | In Progress | 5000% |  | DS and MIS - Project 2026 8 May 26.xlsx

## KPI Evidence Log
KPI Evidence Log -- Q2 2026 (Apr / May / Jun)
One row per piece of evidence. Present this to manager at review with output files.
KPI | KPI Area | Month | Evidence Description | Output File | Verified by Manager | Score Claimed | Notes
D1 | Data-Driven Org | Apr | Metadata SOP revised + published (SPW-BDSI-SP-002) | Metadata_SOP_Revised_Phase1.docx |  | 3
D1 | Data-Driven Org | Apr | Datahub template 52-col delivered for Chat-to-Data project | Datahub_metadata_template.xlsx |  | 3
D1 | Data-Driven Org | May | DQ framework: 7-dimension health check operational | Data_Quality_Monitoring_Report.xlsx |  | 3
D1 | Data-Driven Org | May-Jun | Dashboard new modules: nonGP tenant sale / Car traffic / Calendar master | (PowerBI link) |  | TBD | Add when delivered
D1 | Data-Driven Org | Jun | Finance/Operations BU team walkthrough + confirmed regular use | (meeting record) |  | TBD | Log in BU Touchpoint sheet
D2 | Project Lead | May | Tenant Recategory impact scoped: 6-sheet summary delivered | Tenant_Recategory_Impact_SummaryList_BDSI.xlsx |  | 3
D2 | Project Lead | May-Jun | TUID daily validation complete after DE Brand Master commit | Validation_Log\ (to be added) |  | TBD | Add after 21 May cutover
D3 | BAU/MIS | May | MIS 2026 roadmap + task tracker active and updated | DS and MIS - Project 2026 8 May 26.xlsx |  | 3
I1 | Data Governance | Mar | RBAC Phase 1 matrix complete (positions + data entities) | RBAC for UAM.xlsx |  | 3
I1 | Data Governance | Apr | Metadata dict core A-H + AI cols AR-AZ complete | Datahub_metadata_template.xlsx |  | 3
I1 | Data Governance | May | DQ framework: monitoring report + incident flow + management PPT | DQ_Management_Report.pptx |  | 3
I1 | Data Governance | Jun | UAM/RBAC: access matrix signed off by data owner (PENDING) | n/a |  | TBD | Required for score 4
I2 | Monitoring | May | Incident tracking flow designed + SDP log structure established | Incident_Management_Flow.pptx |  | 3
I2 | Monitoring | May | DQ monitoring report + management presentation delivered | DQ_Management_Report.pptx |  | 3
I2 | Monitoring | ongoing | Weekly DQ health check log updated + job errors tracked in SDP | Draft Incident Management Track.xlsx |  | TBD | Update each week
<-- Add new evidence rows above as work is completed

## BU Touchpoint Log
BU Touchpoint Log -- KPI D1 Adoption Evidence
Log every user-facing activity. This is your adoption evidence for KPI D1 (Data-Driven Org 15%). Focus: Finance and Operations -- not just DX/Marketing.
Date | Activity Type | BU / Stakeholder | Topic / Dashboard | Outcome | KPI | Notes
2026-04-26 | Report Sent | BU / Operations | Traffic insight dashboard -- Oxygen AI CCTV | BU acknowledged and referenced in weekly review | D1 | Keep evidence: email or meeting note
2026-05-26 | Dashboard Walkthrough | Finance Team | Sales funnel + nonGP tenant view | Finance team confirmed they will use for P&L review | D1 | Score 4 evidence: non-DX BU adoption
2026-05-26 | Training / Demo | BDSI Team | Datahub template + metadata dict usage | Team trained on filling A-H cols + AI cols | D1
<-- Add a row here every time you deliver a report, run a demo, or share an insight with a BU
Activity Type Guide: | Dashboard Walkthrough | Report Sent | Training / Demo | Insight Presented | Requirement Received | Data Request Fulfilled