## High Level TImeline (Plan)
| Q1 |  |  | Q2 |  |  |  | Q3 |  | Q4
| Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | OCT
Project | Q1 Mar: • Data governance (RBAC & Policy)
| • Footfall Data Mart (Vendor) | •Footfall- Traffic Profile from CCTV SPD | • PowerBI-CX[44] Traffic to Sale - SPD | • PowerBI -CX[44] Traffic to Sale Conversion |  | •Footfall- Traffic Profile from CCTV SC/SD | • PowerBI-CX[44] Traffic to Sale - SC/SD |  | •Footfall- Traffic Profile from CCTV ICON | • PowerBI-CX[44] Traffic to Sale - ICON
| • Campaign Tracking Pipeline (appflyer) | • PowerBI-CX[43] Customer Insight |  | * PowerBI - CX[43] - Add Traffic and GP sale by builidng* | • PowerBI -New Traffic to sale for K.Wan weekly | •Footfall- Customer profile from event participation
|  |  |  | * Decommission CX[35] with in April | • Data Governance (Meta data )
• Data Governance (Incident management)
• Data Governance (BI Usage log and check process)
|  |  |  | * Data dict for all dashboard - N'Nine CX02 03 09 14 43 44 |  | Chat to data
BAU |  | • PowerBI - CX[02] HNW Port segment | • Superset Partnership Dashboard | • PowerBI -CX[03] Tenant Partnership Tracking | • PowerBI -CX[12] Digital Mall Tracker O2O for champion | • Business Metrics Standardization | • Customer Journey - Campaign Lead to Spending | • Traffic / GP Sales Model | • Enrich Campaign Data (SVOC)
|  | • PowerBI -CX[36] Tenant Champion program tracking | • PowerBI -CX[19] Redesign | • PowerBI -CX[37] Revamp overall performance | • PowerBI -CX[03] Tenant Partnership Tracking (Update Feedback) | • CLV Update (Tier & Coin) | • PowerBI -CX[29] Enhance Acquisition log | • Tenant Pricing Model | • Continued Journey Analytics
|  | • PowerBI -CX[29] Acquisition dashboard (appflyer) | • PowerBI -CX[45] Nextopia | * PowerBI -CX[32] PRH Enhancement | • PowerBI -CX[XX] Tenant Champion O2O for QR Scan | • Customer Journey Zone → Zone | • PwerBI -Data Gap Customers & Spending |  | • App Revamp (Data & Tracking layer – ongoing)
|  |  |  | • PowerBI -CX[14] Campaign Dashboard Enhancement - end of month |  | • PowerBI -CX[19] Customer Service monitoring tracking
• PowerBI -CX[04] Fraud
Dependency | Q1 Jan: • New Tier – Internal Support; Q1 Feb: • Data Pipeline of Dashboard / Report; Q2 Apr: • New Coin (DE deploy 20 ,MIS 21 ) - 21 Data Validation; Q2 May: • App Revamp (IT reserve slot); Q2 June: • New Category (15 Jun 26) VLC+2 week
| • Decommission Dashboard | • Historical GP in VLC Mart |  | • T_uid new mapping logic and redemption mer id | • Footall-Key event evaluation (IT) | Event Tracking: Sample Value(end of may)
Campaign Management Tracking
Mart | Q2 Apr: • [Data Preparation] Car Park Data Reconcile; Q2 May: • PRH Mart understanding (New POS) - Kong; Q2 June: • MART MCARD -Jack; Q2 July: • ย้าย job julab
• [Data Preparation] SC,SD Traffic different from Oxygen AI Dashboard

## Sheet1
Report Name | ETA | Noted | User
• PowerBI -CX[12] Digital Mall Tracker O2O for champion | May | new | DX Digital Mall
• PowerBI -CX[43] Customer Insight | May | enhance -carlendar master
• PowerBI -CX[44] Traffic to Sale - | May | enhance -carlendar master and export page
• PowerBI -CX[03] Tenant Partnership Tracking (Update Feedback) | May | new | DX Customer Service
• PowerBI -CX[XX] Tenant Champion O2O for QR Scan | May | new | DX Customer Service
• PowerBI -CX[XX] Internall Dashboard for K.Wan | May | new | BDSI
• PowerBI -CX[19] Customer Service monitoring tracking | June | enhance -add more logic | DX Customer Service
• PowerBI -CX[04] Fraud | June | enhance -add more data source | DX Fraud
• PowerBI -CX[29] Enhance Acquisition log | Jul | enhance -add more logic | DX Acquisition
• PwerBI -Data Gap Customers & Spending | Jul | new | P'Por (comiitted request?)
Dependency Task for BI Pipeline
• PRH Mart understanding (New POS) - Kong | May |  | PRH
• New Category Revamp (15 Jun 26) VLC+2 week | June |  | DX/ BU
• CarPark | June |  | BDSI

## Incident (hidden)
Type | Category | Subcategory | Item | Free text
Incident | Data Issue | Incomplete Data Incorrect Data Incorrect Logic | PowerBI | report name
|  |  | Superset | report name
|  |  | Other Report | report name
|  |  | Jupyter | job name
|  |  | Airflow | job name
|  |  | VLC DataMart | Schema name
|  |  | SPWG DataWarehouse | Schema name
| System Issue |  | Perx CRM Portal SuperApp Snowplow Huawei Appflyer Kbank | System name
Request | Data Analysis | Data Analysis | Customer & Visitor Data Tenant & Store Data Mall Operations Data Marketing & Campaign Data Financial & Transaction Data Staff Data
| Lead | Lead (Normal Message)
Lead (Need Exclude PDPA)
| Data Support | Data Support
| Dashboard | Usage Training
Dashboard Enhancement
New requirement

## Project (hidden)
No | Type | Group | Topic | Team | Purpose | Progress | Status | Assigned To |  | Expected Timeline | Status | Project Priority | Note | [Internal ] Note
1 | KPI | Bain | App Revamp | XPO | ONESIAM SuperApp revamp aimed at modernizing the codebase, technical architecture, and in-app journey, shifting away from ecommerce and decommissioning tenant chat. The initiative has cross-functional impact on IT and Data teams, especially across app tracking, data pipelines, and analytical capabilities. |  |  | XPO - IT - DS | Tak/Jack | 2026-10-31 |  | Critical / Priority | ** Reqyest consolidate old / new value to be the same format
2 | KPI | Bain | New Category | BU | Update the new leasing category by adjusting and verifying all data sources and models, followed by impact assessment and data validation. |  |  | All | All | 2026-06-30 |  | Bain | **Revisit all dashboard **Audience selection (Campaign management) **Revisit all model (Fraud , segment , cust preference)
3 | KPI | Customer Journey | Synergy on footfalls | BDSI | Analyzing customer journeys across stores and zones to identify synergies, optimize touchpoints, and elevate the overall customer experience as well as the linkage to member spending. |  |  | DS | Lotion/Jack | 2026-04-30 |  | Critical / Priority | ** Owner of project assign to Lotion
4 | KPI | Dashboard | Nextopia | BU-DX | Tracking ecosystem engagement across traffic, Mini App users, membership, Green Points, acquisition, and spending |  |  | DA/MIS | Tee/Jack | 2026-02-15 | Done | Dependency | ** Traffic builidng, zone 5 and 5a, member spending and GP | Hamd on Nextopia data mart
6 | KPI | Dashboard | Executive Dashboard/ Report | BDSI | Develop automated executive dashboards aligned with standardized report formats provided by the DA team |  |  | MIS | Gift/Jack | 2026-03-31 | Done | Critical / Priority | ** CX-[44]
7 | KPI | Dashboard | Customer Journey - Campaign Lead to Spending ( Campaign Tracking Journey) | DX | Developing a customer journey tracking dashboard focused on campaign lead acquisition, conversion, and value |  |  | DS | Tak | 2026-06-01 |  | Critical / Priority
8 | KPI | Dashboard | Superset - Partnership dashboard | DX | Parnership Analysis - Perfeormance and market share |  |  | MIS | Gift/Jack | 2026-03-31 |  | Critical / Priority | ** Need to update on category (May) before migrate to prod on June | Update on current version
9 | BAU | Dashboard | CX[02] - HNW Port segment | DX | Dashboard to have segmenation on ever hnw flag and gp flag | Validation | Done | MIS | Gift/Tee/Jack | 2026-02-15 | Done | BAU Internal |  | TUID in cx[02]
10 | KPI | Dashboard | Member Data Consolidtion | DX | Member Insight Dashboard ( Linkage between all member across SPW – ONESIAM, PlatinuM and Kbank) Linkage to the datamart |  |  | MIS | Tee/Napat | 2026-07-31 |  | Critical / Priority
11 | BAU | Data Availability | Kbank - MID Mapping Automation Process | BDSI | Improving the mapping process between KBank MIDs and ONESIAM tenants to enable more accurate spending capture and attribution |  |  | MIS | Jack | TBC |  | BAU Internal
12 | BAU | Data Availability | Historical GP in VLC mart | BDSI | Create a physical table for historical GP data in VLC Mart instead of using a view, with optimized time-range filtering and query performance |  |  | MIS | Jack | 2026-02-15 | Done | BAU Internal
13 | KPI | Data Availability | Footfalls Datamart | BDSI | Create a Footfall Datamart to Improve Ease of Use for Traffic, Visitor Profiling, and Synergy Analysis |  |  | MIS | Lotion | TBC |  | BAU Internal | ** Pack with Lotion
14 | KPI | Data Availability | PRH Mart after migrate new POS | BDSI | Integrate and validate the PRH datamart after migrating to the new POS, ensuring accurate transaction data and seamless downstream reporting |  |  | DA/MIS | Tee/Jack/Napat | 2026-04-30 |  | BAU Internal | ** Migration Impact | *dependency with DE on finalize the requirement
15 | KPI | Data Availability | Data Gap on Customers and Spending | DX | Create the datamart, linkage, document and dashboard for the customer on each type of loyalty program to see the performance ( ONESIAM, PlatinumM and Kbank) | In Progress | In Progress | DA/MIS | Jack/Napat | 2026-06-30 |  | Critical / Priority | ** Confirm with Ty , K. T
16 | KPI | Data Availability | Campaign Management Data | DX | To integrate the campaign setting and campaign response from CM platform to better track the ROI |  |  | MIS | Jack/Namwan | 2026-10-31 |  | BAU Internal | XPO commit 30-jun-26 Final output : Customer Journey Dashboard
17 | KPI | Data Cabaility | Chat to Data ( Member Data Focus) | BU-IT-BDSI | Partner with IT to evaluate vendors and prepare data foundations for the AI Chat-to-Data project |  |  | MIS | Jack | 2026-06-30 |  | Not Focus
18 | KPI | Data Governance | Business Metrics | BDSI | Establish standardized business metric definitions and calculation logic to improve transparency, consistency, and trust in reporting |  |  | MIS | Gift/Napat | 2026-06-30 |  | Critical / Priority
19 | KPI | Data Governance | Data Access Control | BDSI | Define and formalize data ownership and access guidelines to ensure accountability, security, and proper data usage |  |  | MIS | Gift | 2026-03-31 |  | Critical / Priority
20 | kPI | DX | New Teir (Elite Tier : Top 100) | DX | New Tier for top 100 spender ( interim - soft launch) |  |  | DA/MIS | All | 2026-04-01 |  | Critical / Priority
21 | KPI | External | Telco data with CU | BDSI | Collaborating with the CU team to analyze telco data and uncover behavioral and market trends |  |  | DS | Namwan/New DS | TBC |  | Not Focus
22 | KPI | Internal | New Tier | DX | Support ongoing updates to data pipelines and tier logic to ensure consistency and accuracy |  |  | MIS | Tee/Jack | 2026-01-31 | Done | Critical / Priority
23 | BAU | Internal | standardize data processing structure document and data dictionary | BDSI | Create and maintain a centralized data knowledge reference covering data sources, metrics, and processes to support team members and new joiners |  |  | MIS | Jack | 2026-06-30 |  | BAU Internal
24 | KPI | Internal | Decomisson Dashboard | BDSI | Decommission unused and redundant dashboards to reduce maintenance overhead and improve BI efficiency |  |  | MIS | Gift | 2026-03-31 |  | BAU Internal
25 | BAU | Internal | New Coin | MIS | Support UAT and prepare analytical datasets to compare performance and impact between old and new coin rate structures |  |  | MIS | Jack/T | 2026-04-20 |  | Critical / Priority | **20 Apr Normal rate (19 Apr): IT Validate **21 Apr : VLC Validate **22 Apr: Ready for all report
26 | BAU | Internal | Data Pipeline and Job Standardize Framework | BDSI | Deliver faster time-to-market, minimize operational risk, and ensure smooth compatibility with system migration tasks |  |  | MIS | Jack | TBC |  | BAU Internal
27 | BAU | Migration | Migration from Jupyter Lab to Airflow/ModelArts | BDSI | Sunset JupyterLab-based processes and transition orchestration to Airflow |  |  | DA/MIS | All | TBC |  | BAU Internal
28 | BAU | ML Model | Enrich Campaign Data | DX | Enhance customer preference models by integrating campaign interaction data into the SVOC |  |  | DS | Tak | 2026-10-31 |  | Ideation
29 | KPI | ML Model | Update CLV with new tier and coin | BDSI |  |  |  | DS | Tak | 2026-06-30 |  | BAU Internal
30 | KPI | ML Model | Traffic/ GP sales | BDSI | Build a sales prediction model that incorporates footfall, traffic patterns, and other relevant variables to improve forecast accuracy |  |  | DS | New DS | TBC |  | Critical / Priority
31 | BAU | ML Model | Fraud | DX | Build a classification model to strengthen fraud detection across voucher and coin transactions |  |  | DS | Lotion/Jack | 2026-06-30 |  | Ideation
32 | KPI | ML Model | Tenant Pricing (TBC) | BDSI | Develop a tenant pricing model that incorporates footfall (visits) to ensure leasing prices reflect traffic, store size, and location |  |  | DS | New DS | TBC |  | Critical / Priority
33 | KPI | ML Model | Promotion Recommendation | DX | To deliver personalized promotion recommendations that drive customer engagement, uplift spending, and improve campaign effectiveness. |  |  | DS | Tak | 2026-12-31 |  | Critical / Priority
34 | KPI | ML Model | Customer Journey Zone to Zone, Store to Store | BDSI | Develop machine learning models to learn correlations and patterns across the customer journey, in order to uncover opportunities to increase traffic, drive sales growth, and gain deeper customer insights. |  |  | DS | Lotion | 2026-06-30 |  | Critical / Priority

## IMPACT KPI
KPI No. | Impact KPI | No | Project / Topic | Type | Team | Assignee | Impact KPI (Objective) | Target Timeline | Priority | This Month Focus (Mar 26)
1 | Data Transformation Roadmap | 22 | New Tier – Internal Support | KPI | DX / MIS |  | Data Transformation Roadmap | 2026-01-01 | Critical | Done
2 | Insightful data / information to support decision (Traffic , Sale) | 4 | PowerBI -Nextopia Dashboard | KPI | BU-DX / MIS | Jack / T | Insightful Data to Support Decision | 2026-02-15 | Dependency | Done
3 | Deep Understanding Customer (in-mall & out-mall behavior) | 9 | PowerBI -CX[02] - HNW Port /Zone/New Segment | BAU | DX / MIS |  | Insightful Data to Support Decision | 2026-02-15 | BAU | Done
4 | Insightful data for tenant value co-creation |  | PowerBI -CX[02] - Member Target | BAU | DX / MIS | Jack/Gift | Update DX KPI | 2026-02-20 | BAU | Done
5 | Ease of use (AI / Chat to Data) | 12 | Historical GP in VLC Mart/ GP alignment with 35 | BAU | BDSI / MIS | Jack / T | Data Transformation Roadmap | 2026-02-09 | BAU | Done
|  | 8 | Superset – Partnership Dashboard-QA | KPI | DX / MIS | Gift/Jack | Insightful Data for Tenant Value Co-Creation 2.0 | 2026-03-31 | Critical | In progress (Support POC)
|  |  | PowerBI -ONESIAM Champion program tracking | BAU | DX/ MIS | Gift | Insightful Data for Tenant Value Co-Creation 2.0 | 2026-02-06 | BAU | Done
|  |  | PowerBI -Customer Service monitoring tracking | BAU | DX/ MIS | Gift | Deep Understanding Customer (in-mall & out-mall behavior) | 2026-04-30 | BAU | Hold
|  |  | Enhance Campaing Report CX-09 | BAU | DX/ MIS /DA Support | Gift / Mean | Deep Understanding Customer (in-mall & out-mall behavior) | 2026-02-09 | BAU | Done
|  | 11 | Enhance Data Pipeline of Dashboard / Report | KPI | DX/ MIS | Jack | Data Transformation Roadmap | 2026-02-28 | BAU | Done
|  |  | PowerBI - 29 Fix Job appflyer stop at 21 Jan 2026 | KPI | DX/ MIS | Jack | Data Transformation Roadmap | 2026-02-28 |  | Done
|  | 6 | CX-44 Traffic to Sale -SPD | KPI | BDSI / MIS / DS | Gift/Jack/Lotion | Insightful Data to Support Decision | 2026-03-31 | Critical | Done
|  | 19 | Data Access Control | KPI | BDSI / MIS | Gift | Data Transformation Roadmap | 2026-03-31 | Critical | Done
|  | 15 | Data Gap: Customers & Spending | KPI | DX / DA / MIS | Tak/T | Deep Understanding Customer (In-mall & Out-mall) | 2026-04-01 | Critical | In progress
|  | 20 | New Elite Tier (Top 100) | KPI | DX / DA / MIS |  | Insightful Data for Tenant Value Co-Creation 2.0 | 2026-04-01 | Critical
|  | 10 | Member Data Consolidation | KPI | DX / MIS | Tak/T | Deep Understanding Customer (In-mall & Out-mall) | 2026-04-01 | Critical | Mcard
|  | 25 | New Coin (UAT & Analysis) | BAU | MIS | Jack/T | Insightful Data for Tenant Value Co-Creation 2.0 | 2026-04-20 | Critical | Updated to the lastest timeline
|  | 3 | Synergy on Footfalls | KPI | BDSI / DS | lotion | Deep Understanding Customer (In-mall & Out-mall) | 2026-04-30 | Critical | In progress
|  | 14 | PRH Mart after POS Migration | KPI | BDSI / DA / MIS | Jack | Data Transformation Roadmap | 2026-04-30 | BAU | IT Reconfirm requirement with user
|  | 7 | Customer Journey - Campaign Lead to Spending | KPI | DX / DS | Tak | Insightful Data to Support Decision | 2026-06-01 | Critical | -Aligne Acquisition tracking format with user for future tracking -Prepare O2O Pipeline
|  | 2 | New Category (Leasing) | KPI | BU / DA / MIS |  | Insightful Data for Tenant Value Co-Creation 2.0 | 2026-06-30 | Bain
|  | 16 | Campaign Management Data | KPI | DX / MIS |  | Insightful Data to Support Decision | 2026-06-30 | BAU
|  | 18 | Business Metrics Standardization | KPI | BDSI / MIS |  | Data Transformation Roadmap | 2026-06-30 | Critical
|  | 29 | CLV Update (Tier & Coin) | KPI | BDSI / DS |  | Insightful Data for Tenant Value Co-Creation 2.0 | 2026-06-30 | BAU
|  | 31 | Fraud Detection Model | BAU | DX / DS |  | Data Transformation Roadmap | 2026-06-30 | Ideation
|  | 34 | Customer Journey Zone → Zone | KPI | BDSI / DS |  | Deep Understanding Customer (In-mall & Out-mall) | 2026-06-30 | Critical
|  | 28 | Enrich Campaign Data (SVOC) | BAU | DX / DS |  | Deep Understanding Customer (In-mall & Out-mall) | 2026-10-31 | Ideation
|  | 1 | App Revamp | KPI | XPO / IT / DS |  | Data Transformation Roadmap / Ease of Use (AI-ready) | 2026-10-31 | Critical
|  | 33 | Promotion Recommendation Model | KPI | DX / DS |  | Tenant Value Co-Creation + Customer Insight | 2026-12-31 | Critical
|  | 11 | KBank MID Mapping Automation | BAU | BDSI / MIS |  | Data Transformation Roadmap | TBC | BAU
|  | 13 | Footfalls Datamart | KPI | BDSI / MIS |  | Deep Understanding Customer (In-mall) | TBC | BAU
|  | 17 | Chat to Data (Member Focus) | KPI | BU / IT / BDSI | Jack | Ease of Use (AI / Chat to Data) | TBC | Not Focus | In progress (Support POC)
|  | 21 | Telco Data with CU | KPI | BDSI / DS |  | Deep Understanding Customer (Out-mall) | TBC | Not Focus
|  | 26 | Data Pipeline Standard Framework | BAU | BDSI / MIS |  | Data Transformation Roadmap | TBC | BAU
|  | 27 | Jupyter → Airflow Migration | BAU | BDSI / DA / MIS | Jack | Data Transformation Roadmap | TBC | BAU | Dependency with IT for new python server +2 month for migration effort
|  | 30 | Traffic / GP Sales Model | KPI | BDSI / DS |  | Insightful Data for Tenant Value Co-Creation 2.0 | TBC | Critical
|  | 32 | Tenant Pricing Model | KPI | BDSI / DS |  | Insightful Data for Tenant Value Co-Creation 2.0 | TBC | Critical
|  | 23 | Data Dictionary & Process Doc | BAU | BDSI / MIS |  | Data Transformation Roadmap | TBC | BAU

## Traffic to Sale
#VALUE!
daily
| wtd |  |  | Potentail | Total | Total
| mtd |  |  |  | agg tenant | agg tenant
Target
Actual VS Target
Note: แยก section overall perforamnace (Traffic building only)
Traffic to Sale เอามาทั้งหมด ไม่ต้องสนว่ามีไม่มีกล้อง
Section 2
GP+กล้อง เท่านั้น
| Total | <15 min | >=15 | total
| 100 | 10 | 80 | 90

## Category confirm
|  | Category | Subcategory | Premiumness
Report | Tenant sale & Member dashboard and report | Tenant | Tenant | y | *File tuid master category อันใหม่ |  | Customer Category
Model | Traffic (Oxygen) | Customer |  |  |  | แบ่งเปน 2 เรื่อง
| Customer Segment | Customer |  | y | hold (maintain อันเก่า) | Report | for Validate and prepare segment maintainance (tuid new)
| Customer preference | Customer |  | y |  |  | DX , Front line
| Fraud | Tenant |  | y
[6 empty] | Model | Maintain
Mart | Validate | *ขอ tuid ของ new category ล่วงหน้า ทั้ง Tenant Category & Customer Category
| Category Report | Industry | Sub Industry | Mart
| CX-02 ONESIAM Data Self Service | x | x | "SPWGSPS_VLC".mart_viz_self_service
| CX-03 Tenant Metric Dashboard | x | x | "SPWGSPS_VLC".mart_tenant_transaction
| CX-05 Lead Generation | x | x | "SPWGSPS_VLC".mart_viz_self_service mvss
| CX-09 CRM Portal Redemption Campaign Self Service | - | - | -
| CX-12 Digital Mall Tracker | x | x | "SPWGSPS_VLC".vlc_mart_digital_mall_app_o2o
| CX-14 Campaign Evaluation | - | - | -
| CX-16 PRH Dashboard | - | - | -
| CX-19 COSMOS Dashboard | - | - | -
| CX-29 Acquisition By Channels Dashboard | x | x | "SPWGSPS_VLC".mart_viz_self_service t1
| CX-32 PRH Txn Export | - | - | -
| CX-33 Gift Card Dashboard | - | - | -
| CX-34 Conversion journey Dashboard | - | - | -
| CX-36 ONESIAM Champion Program Tenant Dashboard | x | x | "SPWGSPS_VLC".mart_viz_self_service
| CX-37 Overview of SuperApp Statistic | x | x | "SPWGSPS_VLC".vlc_mart_cx_spending
| CX-43 Member Spending Insight Dashboard (Inc GP Sales) | x | x | "SPWGSPS_VLC".vlc_master_t_uid_profile
| CX-44 Traffic to Sale Conversion | x | x | "SPWGSPS_VLC".vlc_master_t_uid_profile
| Cx-45 Nextopia | - | - | -

## App tracking (hidden)
Overview for App 2.0 New event tracking
Snowpow
Looker
*DE to start pipeline update on xxx

## CATEGORY
ANCHOR
MINI-ANCHOR
IN-LINE
OPEN PLAN
[6 empty] | LUXURY | CART
[6 empty] | NON-LUXURY | VENDING MACHINE
NO. CATE | MAIN CATEGORY | NO. SUB-CATE I | SUB-CATEGORY I | NO. SUB-CATE II | SUB-CATEGORY II | SUB-CATEGORY III | SUB-CATEGORY IV
1 | FASHION & ACCESSORIES | 1.1 | INTERNATIONAL LUXURY | 1.1.1 | READY-TO-WEAR
|  |  |  | 1.1.2 | SHOES
|  |  |  | 1.1.3 | BAGS
|  |  |  | 1.1.4 | SHOES & BAGS
|  |  |  | 1.1.5 | INTERNATIONAL JEWELRY
|  |  |  | 1.1.6 | INTERNATIONAL COSTUME JEWELRY
|  |  |  | 1.1.7 | WATCHES
|  |  |  | 1.1.8 | WATCHES & JEWELRY
|  |  |  | 1.1.9 | EYEWEAR
|  |  |  | 1.1.10 | ACCESSORIES
|  |  |  | 1.1.11 | ALL
|  | 1.2 | BRIDGE | 1.2.1 | READY-TO-WEAR
|  |  |  | 1.2.2 | SHOES
|  |  |  | 1.2.3 | BAGS
|  |  |  | 1.2.4 | SHOES & BAGS
|  |  |  | 1.2.5 | INTERNATIONAL JEWELRY
|  |  |  | 1.2.6 | INTERNATIONAL COSTUME JEWELRY
|  |  |  | 1.2.7 | LOCAL JEWELRY
|  |  |  | 1.2.8 | LOCAL COSTUME JEWELRY
|  |  |  | 1.2.9 | GOLD
|  |  |  | 1.2.10 | WATCHES
|  |  |  | 1.2.11 | WATCHES & JEWELRY
|  |  |  | 1.2.12 | EYEWEAR
|  |  |  | 1.2.13 | ACCESSORIES
|  |  |  | 1.2.14 | UNDERWEAR, LINGERIES, PYJAMAS, SWIMMERS
|  |  |  | 1.2.15 | ALL
|  | 1.3 | FASHION | 1.3.1 | READY-TO-WEAR
|  |  |  | 1.3.2 | SHOES
|  |  |  | 1.3.3 | BAGS
|  |  |  | 1.3.4 | SHOES & BAGS
|  |  |  | 1.3.5 | INTERNATIONAL COSTUME JEWELRY
|  |  |  | 1.3.6 | LOCAL COSTUME JEWELRY
|  |  |  | 1.3.7 | WATCHES
|  |  |  | 1.3.8 | WATCHES & JEWELRY
|  |  |  | 1.3.9 | FASHION EYEWEAR
|  |  |  | 1.3.10 | ACCESSORIES
|  |  |  | 1.3.11 | UNDERWEAR, LINGERIES, PYJAMAS, SWIMMERS
|  |  |  | 1.3.12 | THAI DESIGNER
|  |  |  | 1.3.13 | ALL
|  | 1.4 | SPORT & OUTDOOR | 1.4.1 | READY-TO-WEAR
|  |  |  | 1.4.2 | SHOES
|  |  |  | 1.4.3 | SHOES & BAGS
|  |  |  | 1.4.4 | WATCHES
|  |  |  | 1.4.5 | EYEWEAR
|  |  |  | 1.4.6 | ACCESSORIES
|  |  |  | 1.4.7 | UNDERWEAR, LINGERIES, PYJAMAS, SWIMMERS
|  |  |  | 1.4.8 | OUTDOOR/CAMPING
|  |  |  | 1.4.9 | ALL
|  | 1.5 | SECONDHAND | 1.5.1 | SECONDHAND FASHION
2 | BEAUTY | 2.1 | INTERNATIONAL LUXURY | 2.1.1 | FRAGRANCE
|  |  |  | 2.1.2 | SKINCARE
|  |  |  | 2.1.3 | HAIRCARE
|  |  |  | 2.1.4 | COSMETICS
|  |  |  | 2.1.5 | SPA PRODUCTS
|  |  |  | 2.1.6 | ALL
|  | 2.2 | INTERNATIONAL | 2.2.1 | FRAGRANCE
|  |  |  | 2.2.2 | SKINCARE
|  |  |  | 2.2.3 | SKINCARE & HAIRCARE
|  |  |  | 2.2.4 | COSMETICS
|  |  |  | 2.2.5 | SPA PRODUCTS
|  |  |  | 2.2.6 | ALL
|  | 2.3 | LOCAL | 2.3.1 | FRAGRANCE
|  |  |  | 2.3.2 | SKINCARE
|  |  |  | 2.3.3 | SKINCARE & HAIRCARE
|  |  |  | 2.3.4 | COSMETICS
|  |  |  | 2.3.5 | SPA PRODUCTS
|  |  |  | 2.3.6 | ALL
3 | FOOD & BEVERAGE | 3.1 | COFFEE & TEA | 3.1.1 | COFFEE SPECIALTY
|  |  |  | 3.1.2 | COFFEE MASS
|  |  |  | 3.1.3 | TEA & COFFEE SALON
|  |  |  | 3.1.4 | THAI TEA
|  |  |  | 3.1.5 | CHINESE TEA
|  |  |  | 3.1.6 | GREEN TEA
|  |  |  | 3.1.7 | BUBBLE TEA / MILK TEA / FRUIT TEA
|  |  |  | 3.1.8 | OTHER
|  | 3.2 | ICE CREAM, YOGURT & JUICE | 3.2.1 | ICE CREAM/GELATO/SORBET
|  |  |  | 3.2.2 | SOFT SERVE
|  |  |  | 3.2.3 | JUICE & SMOOTHIE
|  |  |  | 3.2.4 | YOGURT
|  |  |  | 3.2.5 | OTHER
|  | 3.3 | BAKERY, SNACK, SWEET | 3.3.1 | CROISSANT & BAKERY
|  |  |  | 3.3.2 | CAKE & PARTISSERIE
|  |  |  | 3.3.3 | DONUT
|  |  |  | 3.3.4 | POPCORN
|  |  |  | 3.3.5 | COOKIE
|  |  |  | 3.3.6 | SWEET & CANDY
|  |  |  | 3.3.7 | CHOCOLATE
|  |  |  | 3.3.8 | THAI DESSERT
|  |  |  | 3.3.9 | OTHER
|  | 3.4 | FAST FOOD (QSR) | 3.4.1 | BURGER & HOTDOG
|  |  |  | 3.4.2 | FRIED CHICKEN
|  |  |  | 3.4.3 | TACO
|  |  |  | 3.4.4 | FRANCHISE PIZZA
|  |  |  | 3.4.5 | SANDWICH
|  |  |  | 3.4.6 | OTHER
|  | 3.5 | HEALTHY FOOD | 3.5.1 | SALAD
|  |  |  | 3.5.2 | VEGAN
|  |  |  | 3.5.3 | OTHER
|  | 3.6 | BAR & BISTRO | 3.6.1 | COCKTAIL
|  |  |  | 3.6.2 | WINE
|  |  |  | 3.6.3 | BEER
|  |  |  | 3.6.4 | CIGAR
|  |  |  | 3.6.5 | LIVE MUSIC & CLUB
|  |  |  | 3.6.6 | OTHER
|  | 3.7 | WINE & LIQUOR SHOP | 3.7.1 | WINE
|  |  |  | 3.7.2 | LIQUOR SHOP
|  |  |  | 3.7.3 | OTHER
|  | 3.8 | LUXURY DINING | 3.8.1 | LUXURY DINING
|  |  |  | 3.8.2 | FASHION BRANDED DINING
|  |  |  | 3.8.3 | OTHER
|  | 3.9 | ASIAN - THAI | 3.9.1 | ESARN / YUM
|  |  |  | 3.9.2 | NORTHERN
|  |  |  | 3.9.3 | SOUTHERN
|  |  |  | 3.9.4 | CENTRAL
|  |  |  | 3.9.5 | RICE / NOODLES
|  |  |  | 3.9.6 | BUFFET
|  |  |  | 3.9.7 | BBQ
|  |  |  | 3.9.8 | FUSION
|  |  |  | 3.9.9 | OTHER
|  | 3.10 | ASIAN - KOREAN | 3.10.1 | BBQ
|  |  |  | 3.10.2 | FRIED CHICKEN
|  |  |  | 3.10.3 | RICE / NOODLES
|  |  |  | 3.10.4 | VARIETY
|  |  |  | 3.10.5 | BUFFET
|  |  |  | 3.10.6 | OTHER
|  | 3.11 | ASIAN - CHINESE | 3.11.1 | HOT POT
|  |  |  | 3.11.2 | HAINANESE CHICKEN / ROASTED DUCK & PORK
|  |  |  | 3.11.3 | RICE / NOODLES
|  |  |  | 3.11.4 | DIM SUM
|  |  |  | 3.11.5 | BBQ
|  |  |  | 3.11.6 | VARIETY
|  |  |  | 3.11.7 | BUFFET
|  |  |  | 3.11.8 | OTHER
|  | 3.12 | ASIAN - JAPANESE | 3.12.1 | FUSION
|  |  |  | 3.12.2 | SUSHI
|  |  |  | 3.12.3 | OMAKASE
|  |  |  | 3.12.4 | TONKATSU
|  |  |  | 3.12.5 | RICE / NOODLES
|  |  |  | 3.12.6 | SHABU
|  |  |  | 3.12.7 | YAKINIKU
|  |  |  | 3.12.8 | CURRY
|  |  |  | 3.12.9 | IZAKAYA / TEPPANYAKI
|  |  |  | 3.12.10 | VARIETY
|  |  |  | 3.12.11 | BUFFET
|  |  |  | 3.12.12 | OTHER
|  | 3.13 | ASIAN - VIETNAM | 3.13.1 | PHO / SINGLE DISH
|  |  |  | 3.13.2 | VARIETY
|  |  |  | 3.13.3 | OTHER
|  | 3.14 | ASIAN - INDIAN | 3.14.1 | INDIAN CUISINE
|  | 3.15 | ASIAN - MIDDLE EAST | 3.15.1 | MIDDLE EAST CUISINE
|  | 3.16 | ASIAN - OTHER | 3.16.1 | OTHER
|  | 3.17 | WESTERN - ITALIAN | 3.17.1 | PIZZA
|  |  |  | 3.17.2 | PASTA
|  |  |  | 3.17.3 | VARIETY
|  |  |  | 3.17.4 | OTHER
|  | 3.18 | WESTERN - FRENCH | 3.18.1 | FRENCH CUISINE
|  | 3.19 | WESTERN - SPANISH | 3.19.1 | SPANISH CUISINE
|  | 3.20 | WESTERN - MEXICAN | 3.20.1 | MEXICAN CUISINE
|  | 3.21 | WESTERN - OTHER | 3.21.1 | OTHER
|  | 3.22 | STEAK HOUSE | 3.22.1 | LOCAL STEAKHOUSE
|  |  |  | 3.22.2 | INTERNATIONAL STEAKHOUSE
|  | 3.23 | BURGER | 3.23.1 | ASIAN BURGER
|  |  |  | 3.23.2 | WESTERN BURGER
|  | 3.24 | SEAFOOD | 3.24.1 | LOCAL SEAFOOD
|  |  |  | 3.24.2 | INTERNATIONAL SEAFOOD
|  | 3.25 | BUFFET | 3.25.1 | INTERNATIONAL BUFFET
|  | 3.26 | TAKE HOME | 3.26.1 | FOOD
|  |  |  | 3.26.2 | DRINK
|  |  |  | 3.26.3 | DESSERT
|  | 3.27 | FOOD COURT | 3.27.1 | FOOD
|  |  |  | 3.27.2 | DRINK
|  |  |  | 3.27.3 | DESSERT
4 | HEALTH & WELLNESS | 4.1 | BEAUTY CLINIC | 4.1.1 | BEAUTY CLINIC
|  | 4.2 | DENTAL CLINIC | 4.2.1 | DENTAL CLINIC
|  | 4.3 | HAIR TRANSPLANTATION | 4.3.1 | HAIR TRANSPLANTATION
|  | 4.4 | SPA AND MASSAGE | 4.4.1 | SPA AND MASSAGE
|  |  |  | 4.4.2 | ONSEN AND SPA
|  | 4.5 | DRUG STORE & PERSONAL CARE | 4.5.1 | DRUG STORE
|  |  |  | 4.5.2 | DRUG STORE & PERSONAL CARE
|  |  |  | 4.5.3 | OTHERS
|  | 4.6 | GROOMING SERVICE | 4.6.1 | BARBER & HAIR SALON
|  |  |  | 4.6.2 | NAIL SALON
|  |  |  | 4.6.3 | HAIR REMOVAL
|  |  |  | 4.6.4 | EYE LASH & EYE BROW SERVICE
|  |  |  | 4.6.5 | TATTOO
|  |  |  | 4.6.6 | VARIETY
|  |  |  | 4.6.7 | OTHER
|  | 4.7 | HEALTHCARE SERVICE | 4.7.1 | PHYSIOTHERAPY
|  |  |  | 4.7.2 | TRADITIONAL CHINESE MEDICINE
|  |  |  | 4.7.3 | WELLNESS CENTER
|  |  |  | 4.7.4 | ACUPUNCTURE
|  |  |  | 4.7.5 | CHIROPRACTIC
|  |  |  | 4.7.6 | EYE CENTER
|  |  |  | 4.7.7 | FERTILITY & GENETICS
|  |  |  | 4.7.8 | ICE-BATH & CRYO
|  |  |  | 4.7.9 | OTHERS
|  | 4.8 | FITNESS | 4.8.1 | FITNESS
|  |  |  | 4.8.2 | SPECIALTY GYM & STUDIO
5 | LIFESTYLE & LEISURE | 5.1 | PLAY LAND & THEMED ATTRACTION | 5.1.1 | ATTRACTION
|  |  |  | 5.1.2 | PLAY LAND
|  | 5.2 | ENTERTAINMENT | 5.2.1 | CINEMAS
|  |  |  | 5.2.2 | GAME ARCADE
|  |  |  | 5.2.3 | OTHERS
|  | 5.3 | ARTS &TOY | 5.3.1 | ARTS AND COLLECTIBLES
|  |  |  | 5.3.2 | TOYS
|  |  |  | 5.3.3 | ART TOYS
|  | 5.4 | LIFESTYLE STORE | 5.4.1 | LIFESTYLE STORE
|  | 5.5 | MUG AND TUMBLER | 5.5.1 | MUG AND TUMBLER
|  | 5.6 | BOOKS, STATIONERY, ART SUPPLY | 5.6.1 | BOOKS, STATIONERY, ART SUPPLY
|  | 5.7 | CRAFT & SOUVENIR | 5.7.1 | CRAFT & SOUVENIR
|  | 5.8 | MUSICAL INSTRUMENT | 5.8.1 | MUSICAL INSTRUMENT
|  | 5.9 | LUGGAGE & TRAVEL ACCESSORIES | 5.9.1 | LUGGAGE & TRAVEL ACCESSORIES
|  | 5.10 | OPTICAL | 5.10.1 | OPTICAL
|  | 5.11 | FURNITURE & GARDENING | 5.11.1 | INTERNATIONAL
|  |  |  | 5.11. | LOCAL
|  | 5.12 | AUTOMOBILE | 5.12.1 | CAR & MOTOCYCLE & ACCESSORIES
|  | 5.13 | EDUCATION | 5.13.1 | ACADEMIC
|  |  |  | 5.13.2 | SKILLS
|  |  |  | 5.13.3 | SPORT
|  | 5.14 | MOM & KIDS | 5.14.1 | MOM & KIDS
|  | 5.15 | PET SHOP | 5.15.1 | PET SHOP
|  | 5.16 | KITCHEN APPLIANCES | 5.16.1 | KITCHEN APPLIANCES
|  | 5.17 | SECONDHAND | 5.17.1 | SECONDHAND LIFESTYLE
6 | TECHNOLOGY | 6.1 | AUDIO & ENTERTAINMENT | 6.1.1 | AUDIO & ENTERTAINMENT
|  | 6.2 | CAMERA & ACCESSORIES | 6.2.1 | CAMERA & ACCESSORIES
|  | 6.3 | COMPUTER AND MOBILE | 6.3.1 | COMPUTER AND MOBILE
|  | 6.4 | HOME APPLIANCES | 6.4.1 | HOME APPLIANCES
|  | 6.5 | GADGET | 6.5.1 | GADGET
|  | 6.6 | OTHERS | 6.6.1 | OTHERS
7 | SERVICE | 7.1 | FINANCIAL SERVICE | 7.1.1 | ATM
|  |  |  | 7.1.2 | BANK
|  |  |  | 7.1.3 | MONEY EXCHANGE
|  |  |  | 7.1.4 | FINANCIAL SERVICES
|  |  |  | 7.1.5 | OTHERS
|  | 7.2 | AUTO CARE SERVICES | 7.2.1 | CAR WASH
|  |  |  | 7.2.2 | AUTO CARE SERVICES
|  | 7.3 | LAUNDRY SERVICES | 7.3.1 | LAUNDRY SERVICES
|  | 7.4 | FLORISTS | 7.4.1 | FLORISTS
|  | 7.5 | LOCKER & BAGGAGE STORAGE | 7.5.1 | LOCKER & BAGGAGE STORAGE
|  | 7.6 | POSTAL & DELIVERY SERVICE | 7.6.1 | POSTAL & DELIVERY SERVICE
|  | 7.7 | REPAIR AND SERVICES | 7.7.1 | BAG & SHOE REPAIR & CLEANING
|  |  |  | 7.7.2 | CLOTH REPAIR
|  |  |  | 7.7.3 | WATCH REPAIR & KEYCUTTING
|  | 7.8 | OTHERS SERVICES | 7.8.1 | OTHERS SERVICES
|  | 7.9 | SEVICE PROVIDER | 7.9.1 | SEVICE PROVIDER
8 | OTHERS | 8.1 | GROCERY & CONVENIENT STORE | 8.1.1 | GROCERY & CONVENIENT STORE
|  | 8.2 | DEPARTMENT STORE | 8.2.1 | DEPARTMENT STORE
|  | 8.3 | SUPERMARKET | 8.3.1 | SUPERMARKET
|  | 8.4 | OFFICE | 8.4.1 | OFFICE & CO-WORKING SPACE
|  |  |  | 8.4.2 | STAFF ROOM
|  | 8.5 | STORAGE | 8.5.1 | STORAGE
|  | 8.6 | LOUNGE | 8.6.1 | LOUNGE